## ProductBacklog
PRODUCT BACKLOG
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | SB1/US1 | Scrum Member | Create anaconda enviroment | Project will be done on this. | 1 | ST/SJ/SG | 2021-11-30
1 | SB1/US2 | Scrum Member | learn web scraping1 | Fetch data from websites. | 1 | ST | 2021-11-30
1 | SB1/US3 | Scrum Member | Overview yfinance website | To fetch well mannered data | 1 | ST | 2021-11-30
1 | SB1/US4 | Scrum Member | Create multiple tickers | To get data for multiple stocks. | 1 | SJ | 2021-12-07
1 | SB1/US5 | Scrum Member | Using yfinance library. | Get parsed data in json format. | 1 | SJ | 2021-12-07
1 | SB1/US6 | Scrum Member | Using yahoofinancials library | To create multiple tickers.` | 1 | SJ | 2021-12-07
1 | SB1/US7 | Scrum Member | Overview alpha vantage API | to get time interval data of stocks. | 1 | ST | 2021-12-07
1 | SB1/US8 | Scrum Member | Get the free API from alpha vantage | Use the free API to use stocks data. | 1 | ST | 2021-12-07
1 | SB1/US9 | Scrum Member | View Stocks data | Understand the data. | 1 | SG | 2021-12-07
1 | SB1/US10 | Scrum Member | learn web scraping2 | Fetch data in different way | 1 | SG | 2021-12-07
1 | SB1/US11 | Scrum Member | Inspect webpage and identify the tables. | Create code to get that data. | 1 | ST | 2021-12-12
1 | SB1/US12 | Scrum Member | Get beautiful soup library in python | To parse data | 1 | ST | 2021-12-12
1 | SB1/US13 | Scrum Member | Get requests library in python | To send request to webpage. | 1 | ST | 2021-12-12
1 | SB1/US14 | Scrum Member | Write code for web scraping | To get fundamental data of the stocks1 | 1 | SJ | 2021-12-12
1 | SB1/US15 | Scrum Member | Write code for web scraping | To get fundamental data of the stocks2 | 1 | SG | 2021-12-12
1 | SB1/US16 | Scrum Member | Understanding the data | To do data handling and operations. | 1 | ST | 2021-12-12
1 | SB1/US19 | Scrum Member | Performing visualization | To graphically understand the data. | 1 | SG | 2021-12-12
1 | SB1/US20 | Scrum Member | Understanding technical indicators | To perform technical analysis | 1 | ST | 2021-12-12
1 | SB1/US21 | Scrum Member | Learning charting techniques | To perform technical analysis | 1 | ST | 2021-12-12
2 | SB2/US1 | Scrum Member | Overview MACD | we can make use of MACD. | 2 | SG | 2021-12-15
2 | SB2/US2 | Scrum Member | MACD implementation using python | To identify the stock trend. | 2 | SJ | 2021-12-15
2 | SB2/US3 | Scrum Member | Overview of ATR | To perform ATR indicator on stock data. | 2 | ST | 2021-12-15
2 | SB2/US4 | Scrum Member | ATR implementation in python | To identify the stock trend. | 2 | SG | 2021-12-15
2 | SB2/US5 | Scrum Member | Bollingers bands overview | To use Bollingers band in identifying trend. | 2 | SJ | 2021-12-20
2 | SB2/US6 | Scrum Member | Bollingers bands implentation in python | Make practical use of Bollingers Bands | 2 | SJ | 2021-12-20
2 | SB2/US7 | Scrum Member | RSI overview | To understand the use of RSI | 2 | SJ | 2021-12-20
2 | SB2/US8 | Scrum Member | RSI implementation in excel | To practically understand the RSI and make use of it. | 2 | ST | 2021-12-20
2 | SB2/US9 | Scrum Member | RSI implementation in python | Make practical use of relative strength index. | 2 | ST | 2021-12-20
2 | SB2/US10 | Scrum Member | ADX overview | To understand the use of ADX | 2 | ST | 2021-12-20
2 | SB2/US11 | Scrum Member | ADX implementation in excel | To identify the stock trend. | 2 | SJ | 2021-12-20
2 | SB2/US12 | Scrum Member | ADX implementation in python | To integrate functionality of ADX. | 2 | SG | 2021-12-24
2 | SB2/US13 | Scrum Member | Renko overview | To understand the use of Renko. | 2 | ST | 2021-12-24
2 | SB2/US14 | Scrum Member | Renko implementation in python | To graphically visualise the data of stocks in candlestick pattern. | 2 | SJ | 2021-12-24
2 | SB2/US15 | Scrum Member | Ta-Lib overview | Technical indicator library | 2 | ST | 2021-12-24
2 | SB2/US16 | Scrum Member | Ta-lib installation | integrate Ta-lib with anaconda . | 2 | ST | 2021-12-24
2 | SB2/US17 | Scrum Member | Ta-lib application | Use ta-lib indicators using python | 2 | SJ | 2021-12-24
3 | SB3/US1 | Scrum Member | Overview of Performance Measurement - CAGR | I can understand Cumulative Annual Growth Rate | 3 |  | 2021-12-24
3 | SB3/US2 | Scrum Member | Overview of Performance Measurement - Annualized Volatility | I can understand Annualized Volatility | 3 |  | 2022-02-02
3 | SB3/US3 | Scrum Member | Overview of Performance Measurement - Sharpe Ratio/Sortino Ratio | I can understand Sharpe Ratio/Sortino Ratio | 3 |  | 2022-02-03
3 | SB3/US4 | Scrum Member | Overview of Performance Measurement - Maximum Drawdown | I can understand Maximum Drawdown | 3 |  | 2022-02-04
3 | SB3/US5 | Scrum Member | Overview of Performance Measurement - Calmer Ratio | I can understand Calmar Ratio | 3 |  | 2022-02-05
3 | SB3/US6 | Scrum Member | CAGR Implementation in Python | I can use it for evaluation of stocks | 3 |  | 2022-02-05
3 | SB3/US7 | Scrum Member | Volatility Measures Implementation in Python | I can use it for evaluation of stocks | 3 |  | 2022-02-06
3 | SB3/US8 | Scrum Member | Sharpe and Sortino Implementation in Python | I can use it for evaluation of stocks | 3 |  | 2022-02-06
3 | SB3/US9 | Scrum Member | Maximum Drawdown Implementation in Python | I can use it for evaluation of stocks | 3 |  | 2022-02-07
3 | SB3/US10 | Scrum Member | Calmar Ratio Implementation in Python | I can use it for evaluation of stocks | 3 |  | 2022-02-07
3 | SB3/US11 | Scrum Member | Overview of Portfolio Rebalancing | I can understand Backtesting Strategy 1 - Portfolio Rebalancing | 3 |  | 2022-02-08
3 | SB3/US12 | Scrum Member | Overview of Resistance Breakout | I can understand Backtesting Strategy 2 - Resistance Breakout | 3 |  | 2022-02-08
3 | SB3/US13 | Scrum Member | Overview of Renko and OBV | I can understand Backtesting Strategy 3 - Renko and OBV | 3 |  | 2022-02-08
3 | SB3/US14 | Scrum Member | Overview of Renko and MACD | I can understand Backtesting Strategy 4 - Renko and MACD | 3 |  | 2022-02-08
3 | SB3/US15 | Scrum Member | Writing Strategy 1 - Portfolio Rebalancing | To Perform Backtesting | 3 |  | 2022-02-09
3 | SB3/US16 | Scrum Member | Writing Strategy 2 - Resistance Breakout | To Perform Backtesting | 3 |  | 2022-02-09
3 | SB3/US17 | Scrum Member | Writing Strategy 3 - Renko and OBV | To Perform Backtesting | 3 |  | 2022-02-09
3 | SB3/US18 | Scrum Member | Writing Strategy 4 - Renko and MACD | To Perform Backtesting | 3 |  | 2022-02-09
3 | SB3/US19 | Scrum Member | Strategy 1 Implementation in Python | To Identify Accuracy | 3 |  | 2022-02-10
3 | SB3/US20 | Scrum Member | Strategy 2 Implementation in Python | To Identify Accuracy | 3 |  | 2022-02-11
4 | SB4/US1 | Scrum Member | Strategy 3 Implementation in Python | To Identify Accuracy | 4 |  | 2022-02-12
4 | SB4/US2 | Scrum Member | Strategy 4 Implementation in Python | To Identify Accuracy | 4 |  | 2022-02-13
4 | SB4/US3 | Scrum Member | Overview of Magic Formula | I can use the Magic Formula for stocks | 4 |  | 2022-02-14
4 | SB4/US4 | Scrum Member | Overview of Piotroski F-Score | I can use it to know about any company's financial streangth | 4 |  | 2022-02-15
4 | SB4/US5 | Scrum Member | Implementing Magic Formula | I can perform the magic formula analysis | 4 |  | 2022-02-16
4 | SB4/US6 | Scrum Member | Value Investing using Piotroski F-score | I can perform the analysis | 4 |  | 2022-02-17
4 | SB4/US7 | Scrum Member | Learning About Forex Trading | I can Understand Various Types of Forex Trading , stop loss and limit | 4 |  | 2022-02-18
4 | SB4/US8 | Scrum Member | Introduction to FXCM API | To use in Automatic Trading | 4 |  | 2022-02-19
4 | SB4/US9 | Scrum Member | Fetching Data from FXCM API | I can see the Stock Data | 4 |  | 2022-02-20
4 | SB4/US10 | Scrum Member | Introduction to Time module in Python | To use the time module in python | 4 |  | 2022-02-21
4 | SB4/US11 | Scrum Member | Implementing technical indicators in the Automtic Trading System | Used MACD, ATR, slope etc. Functions | 4 |  | 2022-02-21
4 | SB4/US12 | Scrum Member | Defining the trade signal type using trade_signal() function | I can define the signal as sell, buy, close sell and close buy | 4 |  | 2022-02-22
4 | SB4/US13 | Scrum Member | Implementing the main() function | To extract data and get infotmation from it | 4 |  | 2022-02-23
4 | SB4/US14 | Scrum Member | Implementing the time module and closing all trades | Used time module to run the main function | 4 |  | 2022-02-25
4 | SB4/US15 | Scrum Member | Overview of OANDA | Get the info about OANDA web terminal | 4 |  | 2022-02-25
4 | SB4/US16 | Scrum Member | Introduction to OANDA API | Learnt About various OANDA API libraries | 4 |  | 2022-02-25
4 | SB4/US17 | Scrum Member | Fetching Data from API in JASON Format | I can fetch Historical Data | 4 |  | 2022-02-25
4 | SB4/US18 | Scrum Member | Introduction to SMA Crossover strategy | Learn about SMA Crossover strategy of Forex Trading | 4 |  | 2022-02-26
4 | SB4/US19 | Scrum Member | Implementation of SMA Crossover strategy with OANDA API | I can use the data for crossovers | 4 |  | 2022-02-26
4 | SB4/US20 | Scrum Member | Testing of Automated Trading System | I can test and verify the results | 4 |  | 2022-02-26

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Digital College>
SB1/US1 | As a Student I want to Create anaconda enviroment so that Project will be done on this. | SB1/US1/T1 | Study the documentation of anaconda | SJ | Not Started | 2021-11-30
|  | SB1/US1/T2 | download anaconda | ST | Not Started | 2021-11-30
|  | SB1/US1/T3 | setting up anaconda account | SJ | Not Started | 2021-11-30
|  | SB1/US2/T2 | Designing of Email(to be send) | SM | Not Started | 2021-11-30
|  | SB1/US2/T3 | Send Email via coding using the Mandrill App | SP | Not Started | 2021-11-30
|  | SB1/US2/T4 | Connection with database to update the status in the database. | RA | Not Started | 2021-11-30
SB1/US2 | As a Student I want to learn web scraping1 so that Fetch data from websites. | SB1/US2/T1 | Study on investopedia | SG | Not Started | 2021-11-30
|  | SB1/US2/T2 | code program to fetch data | SJ | Not Started | 1900-01-01
|  | SB1/US2/T3 | use Yahoofinance to fetch data | SJ | Not Started | 2021-11-30
|  | SB1/US2/T4 | Check user valid or not (connecting the database) | RM | Not Started | 2021-11-30
|  | SB1/US2/T5 | Testing of the module on localhost and then on server. | RA+SP+PB+RM | Not Started | 2021-11-30
SB1/US3 | As a Student I want to Overview yfinance website so that To fetch well mannered data | SB1/US3/T6 | going to website for open library | SG | Not Started | 2021-11-30
|  | SB1/US3/T7 | downloading modules to anaconda env. | SG | Not Started | 2021-11-30
|  | SB1/US2/T8 | coding and using built-in functions to fetch data. | RA | Not Started | 2021-11-30
|  | SB1/US2/T9 | Connection with database to update the status in the database. | ST | Not Started | 2021-11-30
SB1/US4 | Aa a Student I want to Create multiple tickers so that To get data for multiple stocks. | SB1/US4/T10 | update the code of web scraping for multiple stocks data. | SJ | Not Started | 2021-12-07
|  | SB1/US4/T11 | validate user input for stocks ticker in proper manner. | ST | Not Started | 2021-12-07
|  | SB1/US4/T12 | test code for proper output | SJ | Not Started | 2021-12-07
|  | SB1/US2/T13 | Connection with database to update the status in the database. | RM | Not Started | 2021-12-07
|  | SB1/US2/T14 | Testing of the module on localhost and then on server. | RA+SP+PB+RM | Not Started | 2021-12-07
SB1/US5 | Aa a Student I wantto Using yfinance library so that Get parsed data in json format. | SB1/US5/T15 | importing modules of yfinance library. | SG | Not Started | 2021-12-07
|  | SB1/US5/T16 | coding and using built-in functions to fetch data. | ST | Not Started | 2021-12-07
|  | SB1/US5/T17 | veryfing proper input for stocks ticker. | SJ | Not Started | 2021-12-07
|  | SB1/US5/T18 | testing code at user level. | ST | Not Started | 2021-12-07
SB1/US6 | Aa a Student I want to Use yahoofinancials library so that To create multiple tickers.` | SB1/US6/T19 | update the code for multiple data for tickers nusing yfinance library. | SJ | Not Started | 2021-12-07
|  | SB1/US6/T20 | validate user for proper input for multiple data. | SG | Not Started | 2021-12-07
|  | SB1/US6/T21 | test code for proper output | SG | Not Started | 2021-12-07
|  | SB1/US2/T22 | Testing of the module on localhost and then on server. | ST | Not Started | 2021-12-07
SB1/US7 | Aa a Student I want to Overview alpha vantage API so that to get time interval data of stocks. | SB1/US7/T23 | look for thew free API at alpha vantage website. | SJ | Not Started | 2021-12-07
|  | SB1/US7/T24 | create demo account for free API. | ST | Not Started | 2021-12-07
|  | SB1/US7/T25 | Copy key for free API access in local host. | SG | Not Started | 2021-12-07
|  | SB1/US7/T26 |  | SG | Not Started | 2021-12-07
SB1/US8 | Aa a Student I wantto Get the free API from alpha vantage so that Use the free API to use stocks data. | SB1/US8/T27 | Use key for free API in code. | SG | Not Started | 2021-12-07
|  | SB1/US8/T28 | using key access data. | SJ | Not Started | 2021-12-07
|  | SB1/US8/T29 | Convert json format data into panda dataframe. | SJ | Not Started | 2021-12-07
|  | SB1/US8/T30 | test code for proper output | SJ | Not Started | 2021-12-07
SB1/US9 |  | SB1/US2/T31 | Connection with Database to insert the record. | RA+SP+PB+RM | Not Started | 2021-12-07
| Aa a Student I wantto View Stocks data so that Understand the data. | SB1/US9/T32 | analyze stocks data for anamolies. | SG | Not Started | 2021-12-07
|  | SB1/US9/T33 | do data handling. | SG | Not Started | 2021-12-07
|  | SB1/US9/T34 | update nan values. | SJ | Not Started | 2021-12-07
|  | SB1/US9/T35 | do data rolling operation. | ST | Not Started | 2021-12-12
SB1/US10 |  | SB1/US2/T36 | Testing of the module on localhost and then on server. | SJ | Not Started | 2021-12-12
| Aa a Student I wantto learn web scraping2 so that Fetch data in different way | SB1/US10/T37 | Fetch Data withpout using API or library. | ST | Not Started | 2021-12-12
|  | SB1/US10/T38 | Look for the website from which we are allowed to scrape website. | SG | Not Started | 2021-12-12
|  | SB1/US10/T39 | append “/robots. txt” to the end of the URL of the website. | ST | Not Started | 2021-12-12
|  | SB1/US10/T40 | veryfying the website for data scraping. | SJ | Not Started | 2021-12-12
SB1/US11 | Aa a Student I wantto Inspect webpage and identify the tables so that Create code to get that data. | SB1/US11/T41 | Enter any URL for searching a website ex yahoofinnancials. | ST | Not Started | 2021-12-12
|  | SB1/US11/T42 | inspect page using inspect option in chrome. | SP | Not Started | 2021-12-12
|  | SB1/US11/T43 | see robot.txt file to verify web scraping is allowed or not. | SJ | Not Started | 2021-12-12
|  | SB1/US11/T44 | seacrh for table attributes in inspect page and copy table attribute class. | SG | Not Started | 2021-12-12
SB1/US12 | Aa a Student I wantto Get beautiful soup library in python so that To parse data. | SB1/US12/T45 | read documentation of beautiful soup. | SJ | Not Started | 2021-12-12
|  | SB1/US12/T46 | download modules for beautiful soup library. | SJ | Not Started | 2021-12-12
|  | SB1/US12/T47 | veryfying library using anaconda prompt. | SG | Not Started | 2021-12-12
|  | SB1/US2/T48 | Validating user input at server level | RA+SP+PB+RM | Not Started | 2021-12-12
SB1/US13 | Aa a Student I wantto Get requests library in python so that To send request to webpage. | SB1/US13/T49 | read documentation of requests library for python. | SG | Not Started | 2021-12-12
|  | SB1/US13/T50 | download modules for requests library. | SG | Not Started | 2021-12-12
|  | SB1/US13/T51 | verify library resources using anaconda prompt | ST | Not Started | 2021-12-12
SB1/US14 | Aa a Student I want to Write code for web scraping so that To get fundamental data of the stocks1. | SB1/US14/T52 | import beautiful soup modules in jupyter notebook | ST | Not Started | 2021-12-12
|  | SB1/US14/T53 | import requests modules in jupyter notebook. | SJ | Not Started | 2021-12-12
|  | SB1/US14/T54 | code for single stock. | ST | Not Started | 2021-12-12
|  | SB1/US14/T55 | verify and test code. | SJ | Not Started | 2021-12-12
SB1/US15 | Aa a Student I want to Write code for web scraping so that To get fundamental data of the stocks2. | SB1/US15/T56 | update the code for multiple tickers. | SG | Not Started | 2021-12-12
|  | SB1/US15/T57 | validate the code | SJ | Not Started | 2021-12-12
|  | SB1/US15/T58 | test the code at user level. | SG | Not Started | 2021-12-12
SB1/US16 | As a student I want to Understanding the data so that To do data handling and operations. | SB1/US16/T59 | load the data in jupyter notebo0ok | ST | Not Started | 2021-12-12
|  | SB1/US16/T60 | read the data to understand | SJ | Not Started | 2021-12-12
|  | SB1/US16/T61 | handle nan values | ST | Not Started | 2021-12-12
|  | SB1/US16/T62 | perform data rolling operation. | SJ | Not Started | 2021-12-12
SB1/US17 | As a student I want to Performing visualization so that To graphically understand the data. | SB1/US17/T63 | graphically visualize the stock data. | SG | Not Started | 2021-12-12
|  | SB1/US17/T64 | look for key indicatiors using graphs and plots. | SG | Not Started | 2021-12-12
SB1/US18 | As a student I want to Understanding technical indicators so that To perform technical analysis. | SB1/US18/T65 | access zerodha varsity platfrom for understanding. | ST | Not Started | 2021-12-12
|  | SB1/US18/T66 | perform technical analysis on historical data. | SJ | Not Started | 2021-12-12
|  | SB1/US18/T67 | selecting key indicators we want to use. | ST | Not Started | 2021-12-12
|  | SB1/US18/T68 | testing them again on historical data/forex data. | SG | Not Started | 2021-12-12
SB1/US19 | As a student I want to Learning charting techniques so that To perform technical analysis. | SB1/US19/T69 | learn basics about candlesticks pattern. | SG | Not Started | 2021-12-12
|  | SB1/US19/T70 | understand high,low,close,open in candlestick pattern. | SG | Not Started | 2021-12-12
|  | SB1/US19/T71 | look for patterns in chart of historical data. | SJ | Not Started | 2021-12-12
|  | SB1/US19/T72 | test results. | SJ | Not Started | 2021-12-12

## SB BD Ch01
Spring Backlog 01 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2021-12-12 | 67 | 0 | Tasks
2021-12-07 | 31 | 0
2021-11-30 | 9 | 0
Days

## sprintbacklog2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Digital College>
SB2/US1 | As a Student I want to Overview MACD so that we can make use of MACD. | SB2/US1/T1 | Go to investopedia website | SG | Not Started | 2021-12-15
|  | SB2/US1/T2 | learn techniques for MACD. | SJ | Not Started | 2021-12-15
|  | SB2/US1/T3 | Technically implement MACD in charts | ST | Not Started | 2021-12-15
SB2/US2 | As a Student I want to MACD implementation using python so that To identify the stock trend. | SB2/US2/T7 | import yfinance module | ST | Not Started | 2021-12-15
|  | SB2/US2/T8 | download data using yfinance | SJ | Not Started | 2021-12-15
|  | SB2/US2/T9 | make MACD function | SJ | Not Started | 2021-12-15
SB2/US3 | As a Student I want to Overview of ATR so that To perform ATR indicator on stock data. | SB2/US3/T12 | Go to investopedia website | SG | Not Started | 2021-12-15
|  | SB2/US3/T13 | learn ATR functionality | ST | Not Started | 2021-12-15
|  | SB2/US3/T14 | Technically implement ATR in charts | SJ | Not Started | 2021-12-15
SB2/US4 | Aa a Student I want to ATR implementation in python so that To identify the stock trend. | SB2/US1/T16 | import yfinance module | ST | Not Started | 2021-12-15
|  | SB2/US1/T17 | download data using yfinance | SJ | Not Started | 2021-12-15
|  | SB2/US1/T18 | make ATR function | SJ | Not Started | 2021-12-15
|  | SB2/US1/T19 | test results | SG | Not Started | 2021-12-15
SB2/US5 | Aa a Student I want to Bollingers bands overview so that To use Bollingers band in identifying trend. | SB2/US1/T21 | open zerodha varsity app | SG | Not Started | 2021-12-20
|  | SB2/US1/T22 | learn basics for bollingers bands | SJ | Not Started | 2021-12-20
|  | SB2/US1/T23 | technically understand using charts | SG | Not Started | 2021-12-20
SB2/US6 | Aa a Student I wantto Bollingers bands implentation in python so that Make practical use of Bollingers Bands | SB2/US1/T25 | import yfinance module | ST | Not Started | 2021-12-20
|  | SB2/US1/T26 | download data using yfinance | ST | Not Started | 2021-12-20
|  | SB2/US1/T27 | make function for bollinger band | SJ | Not Started | 2021-12-20
|  | SB2/US1/T28 | test results | SG | Not Started | 2021-12-20
SB2/US7 | Aa a Student I wantto RSI overview so that To understand the use of RSI. | SB2/US1/T30 | open zerodha varsity app | SG | Not Started | 2021-12-20
|  | SB2/US1/T31 | learn basics about RSI | ST | Not Started | 2021-12-20
|  | SB2/US1/T32 | technically understand using charts | ST | Not Started | 2021-12-20
SB2/US8 | Aa a Student I want to RSI implementation in excel so that To practically understand the RSI and make use of it. | SB2/US1/T34 | import data in excel | ST | Not Started | 2021-12-20
|  | SB2/US1/T35 | make RSI formula | SG | Not Started | 2021-12-20
|  | SB2/US1/T36 | test results | ST | Not Started | 2021-12-20
SB2/US9 | Aa a Student I wantto RSI implementation in python so that Make practical use of relative strength index. | SB2/US1/T38 | import yfinance module | SG | Not Started | 2021-12-20
|  | SB2/US1/T39 | download data using yfinance | ST | Not Started | 2021-12-20
|  | SB2/US1/T40 | make RSI function | SJ | Not Started | 2021-12-20
|  | SB2/US1/T41 | test and verify results | ST | Not Started | 2021-12-20
SB2/US10 | Aa a Student I wantto ADX overview so that To understand the use of ADX. | SB2/US1/T43 | open zerodha varsity app | SJ | Not Started | 2021-12-20
|  | SB2/US1/T44 | learn basics about ADX | ST | Not Started | 2021-12-20
|  | SB2/US1/T45 | technically understand using charts | SG | Not Started | 2021-12-20
SB2/US11 | Aa a Student I wantto ADX implementation in excel so that To identify the stock trend. | SB2/US1/T48 | import data in excel | SG | Not Started | 2021-12-20
|  | SB2/US1/T49 | make ADX formula | SJ | Not Started | 2021-12-20
|  | SB2/US1/T50 | test results | SG | Not Started | 2021-12-20
SB2/US12 | Aa a Student I wantto ADX implementation in python so that To integrate functionality of ADX. | SB2/US1/T52 | import yfinance module | SG | Not Started | 2021-12-24
|  | SB2/US1/T53 | download data using yfinance | ST | Not Started | 2021-12-24
|  | SB2/US1/T54 | make RSI function | ST | Not Started | 2021-12-24
|  | SB2/US1/T55 | test and verify results | ST | Not Started | 2021-12-24
SB2/US13 | Aa a Student I wantto Renko overview so that To understand the use of Renko. | SB2/US1/T56 | read documentation of renko | SG | Not Started | 2021-12-24
|  | SB2/US1/T57 | learn to understand renko charts | SJ | Not Started | 2021-12-24
|  | SB2/US1/T58 | download stocktrends modules for renko | SJ | Not Started | 2021-12-24
SB2/US14 | Aa a Student I wantto Renko implementation in python so that To graphically visualise the data of stocks in candlestick pattern. | SB2/US1/T61 | import yfinance module | ST | Not Started | 2021-12-24
|  | SB2/US1/T62 | download data using yfinance | SG | Not Started | 2021-12-24
|  | SB2/US1/T63 | import renko from stocktrends | SJ | Not Started | 2021-12-24
|  | SB2/US1/T64 | make ATR function | ST | Not Started | 2021-12-24
|  | SB2/US1/T65 | make renko function | SJ | Not Started | 2021-12-24
SB2/US15 | Aa a Student I want to Ta-Lib overview so that make use of Technical indicator library | SB2/US1/T66 | study about ta-lib form git-hub. | SG | Not Started | 2021-12-24
|  | SB2/US1/T67 | learn how to use python wrapper | SJ | Not Started | 2021-12-24
|  | SB2/US1/T68 | learn various indicators. | ST | Not Started | 2021-12-24
SB2/US16 | Aa a Student I want to Ta-lib installation so that integrate Ta-lib with anaconda . | SB2/US1/T70 | install ta-lib files and modules from git-hub. | SG | Not Started | 2021-12-24
|  | SB2/US1/T71 | update them in conda env. | SJ | Not Started | 2021-12-24
|  | SB2/US1/T72 | test by importing them in jupyter. | ST | Not Started | 2021-12-24
SB2/US17 | As a student I want to use Ta-lib so that Use ta-lib indicators in python. | SB2/US1/T74 | import numpy | SJ | Not Started | 2021-12-24
|  | SB2/US1/T75 | import alpha vantage time series | SG | Not Started | 2021-12-24
|  | SB2/US1/T76 | import talib | ST | Not Started | 2021-12-24
|  | SB2/US1/T77 | use talib functions for technical indicators | SG | Not Started | 2021-12-24
|  | SB2/US1/T78 | verify results | ST | Not Started | 2021-12-24

## SB BD Ch02
Spring backlog 2 Burnt Down chart
Date | Planned Total Task | Actual Uncompleted Task
2021-12-15 | 13 | 0 | Tasks
2021-12-20 | 36 | 0
2021-12-24 | 59 | 0
Days

## sprintbacklog3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3 - <Digital College>
SB3/US1 | I want to Overview of Performance Measurement - CAGR so that I can understand Cumulative Annual Growth Rate | SB3/US1/T1 | Study of Performance Measurement | ST | NOT STARTED | 2022-02-04
|  | SB3/US1/T2 | Learning about CAGR | SJ | NOT STARTED | 2022-02-04
2022-02-04
SB3/US2 | I want to Overview of Performance Measurement - Annualized Volatility so that I can understand Annualized Volatility | SB3/US2/T1 | Study of Annualized Volatility | SG | NOT STARTED | 2022-02-04
|  | SB3/US2/T2 | Importance of Annualized Volatility in Stocks | SJ | NOT STARTED | 2022-02-04
2022-02-04
SB3/US3 | I want to Overview of Performance Measurement - Sharpe Ratio/Sortino Ratio so that I can understand Sharpe Ratio/Sortino Ratio | SB3/US3/T1 | Study of Sharpe Ratio | ST | NOT STARTED | 2022-02-04
|  | SB3/US3/T2 | Study of Sortino Ratio | SJ | NOT STARTED | 2022-02-04
|  | SB3/US3/T3 | Importance of Sharpe/Sortino Ratio in Stocks | SJ | NOT STARTED | 2022-02-04
SB3/US4 | I want to Overview of Performance Measurement - Maximum Drawdown so that I can understand Maximum Drawdown | SB3/US4/T1 | Study of Maximum Drawdown | SG | NOT STARTED | 2022-02-04
|  | SB3/US4/T2 | Importance of Maximum Drawdown in Stocks | ST | NOT STARTED | 2022-02-04
2022-02-04
SB3/US5 | I want to Overview of Performance Measurement - Calmer Ratio so that I can understand Calmer Ratio | SB3/US5/T1 | Study of Calmer Ratio | ST | NOT STARTED | 2022-02-04
|  | SB3/US5/T2 | Importance of Calmer Ratio in Stocks | SJ | NOT STARTED | 2022-02-04
2022-02-04
SB3/US6 | I want CAGR Implementation in Python so that I can use it for evaluation of stocks | SB3/US6/T1 | Use Python to Implement the CAGR | SG | NOT STARTED | 2022-02-04
|  | SB3/US6/T2 | Testing CAGR with Stock Data | SG | NOT STARTED | 2022-02-04
2022-02-04
SB3/US7 | I want Volatility Measures Implementation in Python so that I can use it for evaluation of stocks | SB3/US7/T1 | Use Python to Implement the Volatility Measures | SG | NOT STARTED | 2022-02-04
|  | SB3/US7/T2 | Testing Volatility Measures with Stock Data | ST | NOT STARTED | 2022-02-08
|  |  |  | SJ |  | 2022-02-08
SB3/US8 | I want Sharpe and Sortino Implementation in Python so that I can use it for evaluation of stocks | SB3/US8/T1 | Use Python to Implement the Sharpe and Sortino | SJ | NOT STARTED | 2022-02-08
|  | SB3/US8/T2 | Testing Sharpe and Sortino with Stock Data | SG | NOT STARTED | 2022-02-08
|  |  |  | SJ |  | 2022-02-08
SB3/US9 | I want Maximum Drawdown Implementation in Python so that I can use it for evaluation of stocks | SB3/US9/T1 | Use Python to Implement the Maximum Drawdown | ST | NOT STARTED | 2022-02-08
|  | SB3/US9/T2 | Testing Maximum Drawdown with Stock Data | ST | NOT STARTED | 2022-02-08
|  |  |  | SJ |  | 2022-02-08
SB3/US10 | I want Calmar Ratio Implementation in Python so that I can use it for evaluation of stocks | SB3/US10/T1 | Use Python to Implement the Calmar Ratio | SJ | NOT STARTED | 2022-02-08
|  | SB3/US10/T2 | Testing Calmar Ratio with Stock Data | SG | NOT STARTED | 2022-02-08
|  |  |  | ST |  | 2022-02-08
SB3/US11 | I want to Overview of Portfolio Rebalancing so that I can understand Backtesting Strategy 1 - Portfolio Rebalancing | SB3/US11/T1 | Study of Backtesting | SJ | NOT STARTED | 2022-02-08
|  | SB3/US11/T2 | Learning about Portfolio Rebalancing and its Importance | ST | NOT STARTED | 2022-02-08
|  |  |  | SJ |  | 2022-02-08
SB3/US12 | I want to Overview of Resistance Breakout so that I can understand Backtesting Strategy 2 - Resistance Breakout | SB3/US12/T1 | Study of Resistance Breakout | SJ | NOT STARTED | 2022-02-08
|  | SB3/US12/T2 | Importance of Resistance Breakout in Stocks | SG | NOT STARTED | 2022-02-08
SG
SB3/US13 | I want to Overview of Renko and OBV so that I can understand Backtesting Strategy 3 - Renko and OBV | SB3/US13/T1 | Study of Renko and OBV | SJ | NOT STARTED | 2022-02-12
|  | SB3/US13/T2 | Importance of Renko and OBV in Stocks | SG | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US14 | I want to Overview of Renko and MACD so that I can understand Backtesting Strategy 4 - Renko and MACD | SB3/US14/T1 | Study of Renko and MACD | SJ | NOT STARTED | 2022-02-12
|  | SB3/US14/T2 | Importance of Renko and MACD in Stocks | SJ | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US15 | I want to Write Strategy 1 - Portfolio Rebalancing To Perform Backtesting | SB3/US15/T1 | Documenting Backtesting Strategy 1 | SJ | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US16 | I want to Write Strategy 2 - Portfolio Rebalancing To Perform Backtesting | SB3/US16/T1 | Documenting Backtesting Strategy 2 | SJ | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US17 | I want to Write Strategy 3 - Portfolio Rebalancing To Perform Backtesting | SB3/US17/T1 | Documenting Backtesting Strategy 3 | ST | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US18 | I want to Write Strategy 4 - Portfolio Rebalancing To Perform Backtesting | SB3/US18/T1 | Documenting Backtesting Strategy 4 | ST | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US19 | I want Strategy 1 Implementation in Python so that To Identify Accuracy | SB3/US19/T1 | Use Python to Implement the Strategy 1 | ST | NOT STARTED | 2022-02-12
|  | SB3/US19/T2 | Testing Strategy 1 with Stock Data | SG | NOT STARTED | 2022-02-12
|  |  |  | SJ |  | 2022-02-12
SB3/US20 | I want Strategy 2 Implementation in Python so that To Identify Accuracy | SB3/US520/T1 | Use Python to Implement the Strategy 2 | SG | NOT STARTED | 2022-02-12
|  | SB3/US20/T2 | Testing Strategy 2 with Stock Data | SG | NOT STARTED | 2022-02-12
SJ

## SB BD ch03
Spring Backlog 03 burn down chart
Date | Planned Total Task | Actual Incompleted Task
2022-02-04 | 14 | 0 | Tasks
2022-02-08 | 25 | 0
2022-02-12 | 38 | 0
Days

## SprintBacklog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4 - <Digital College>

## SB BD Ch04
Date | Planned Total Task | Actual Uncompleted Task
2017-10-12 | 177 | 190 | Tasks
2017-10-24 | 110 | 150
2017-10-26 | 80 | 100
2017-10-28 | 25 | 16
2017-11-01 | 15 | 15
2017-11-02 | 0 | 0
0
Days